## Instructions
#VALUE!
BEAD Project Milestone Schedule — Instructions
Kansas Office of Broadband Development (KOBD) September 2026 (version 1.0)
NTIA Guidance:
Each subrecipient must create a milestone schedule identifying project timelines including, as required, the completion of NEPA, the completion of consultations including National Historic Preservation Act (NHPA) Section 106 and Endangered Species Act (ESA) Section 7, and state and local permits. Schedules should reflect typical NEPA document durations as noted below. Please see the sheet labeled "Sample" for an example milestone schedule for a project that qualifies for a Categorical Exclusion. In addition to identifying specific deadlines and durations, the Subrecipient must also provide a narrative (as relevant) describing the completion of consultations, NEPA and Section 106 reviews, and submission of EHP documentation. This workbook is due to KOBD within 30 days after contract execution. It supplements (and does not replace) the KOBD ESAPTT Screening Questionnaire referenced in KOBD's BEAD EHP Guidance. Finally, it must be updated as needed.
NEPA for BEAD: Milestone Schedule and NEPA Timeline
| Categorical Exclusion (CATEX): |  | ~3–6 months
| Environmental Assessment (EA): |  | ~6–12 months
| Environmental Impact Statement (EIS)*: |  | >12 months (NTIA will advise on preparation timelines if an EIS is required)
Milestone Schedule Instructions
| Step 1 | Open the sheet "Subrecipient Milestone Schedule."
| Step 2 | Enter the Project Start Date, Project Name, BEAD Project ID, and NEPA Project ID # in the yellow cells near the top.
| Step 3 | Review the pre-filled Kansas BEAD activities, organized into four phase groups modeled on NTIA's milestone schedule example: Project Design & Initiation; Tribal Coordination & Agency Engagement; Environmental Review & Consultations; and Permits & Authorizations. Add project-specific activities below the last group as needed.
| Step 4 | Once needed permits have been identified, copy the "Permit #" example rows near the bottom of the Permits & Authorizations group — one row per specific permit (e.g., a KDOT permit, a local utility permit) — and rename/fill in each one.
| Step 5 | Provide a narrative in the Narrative column describing your approach to completing each activity.
| Step 6 | Use the Remarks column to note any specific challenges or gating items for that activity.
| Step 7 | Fill in Baseline Start and Baseline End the first time the schedule is set, and do not change them afterward. Fill in Current Start and Current End for the schedule as it stands today, and update these two columns whenever the schedule changes. Duration (business days) auto-calculates from the Current dates.
| Step 8 | The Activity Timeline shading is automatic: it compares the Baseline and Current dates for you (blue = on track, orange = added/slipped since Baseline, gray = Baseline only). Do not manually shade these cells.
| Note | Do not insert or delete rows — this may cause formatting and formula errors.
<more>
Milestone Schedule Activities
GROUP 1: PROJECT DESIGN & INITIATION
| ✓ | Subrecipient award and project initiation
| ✓ | Subrecipient obtains expertise for NEPA, NHPA, and Section 7 reviews
| ✓ | NEPA Project Area Approval
GROUP 2: TRIBAL COORDINATION & AGENCY ENGAGEMENT
| ✓ | Subrecipient provides project information to KOBD to initiate Tribal notification through the Project Description tab of the KOBD ESAPTT Screening Questionnaire
| ✓ | Pre-application meetings with permitting agencies
GROUP 3: ENVIRONMENTAL REVIEW & CONSULTATIONS
| ✓ | Conduct resource screening to support completion of the Extraordinary Circumstances tab of the ESAPPT Screening Questionnaire
| ✓ | Conduct ESA Section 7 obligations (NTIA “No Effect” list, IPaC, Biological Assessment, USFWS-Kansas / KDWP consultation)
| ✓ | Conduct Section 106 process, including Kansas SHPO consultation
| ✓ | Screen and address water resources (wetlands, streams, floodplains); pursue USACE Section 404/408 and KDHE Section 401 authorizations as applicable
| ✓ | NEPA level determined
| ✓ | Complete and submit EHP package (ESAPTT Screening Questionnaire and relevant material) to KOBD
| ✓ | Receive NEPA decision document / Notice to Proceed
GROUP 4: PERMITS & AUTHORIZATIONS
| ✓ | Identify required local, state, and federal permits
| ✓ | Begin state and local permit applications
| ✓ | Finalize remaining permits and private authorizations

## Sample
Kansas BEAD Milestone Schedule
In addition to identifying specific deadlines and durations, the Subrecipient must also provide a narrative (as relevant) describing the completion of consultations, NEPA and Section 106 reviews, and submission of EHP documentation. This schedule reflects NTIA's preferred milestone schedule format: timeframes are tracked in months relative to project award, rather than calendar dates. A Milestone Schedule for a BEAD program project may include additional activities not represented on this sample schedule; populate applicable information in empty, pre-formatted rows below as needed. Finally, a Milestone Schedule must be updated as needed.
| Project Start Date: |  |  |  | 2026-01-05
| Project Name: |  |  |  | EXAMPLE PROJECT — Categorical Exclusion
| BEAD Project ID: |  |  |  | KS-BEAD-000
| NEPA Project ID #: |  |  |  | NEPA-000
[10 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
[10 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[10 empty] | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
| # | Activity | Narrative | Remarks | Baseline Start | Baseline End | Current Start | Current End | Duration (business days) | 2026-01-01: Activity Timeline — shading is automatic based on the Baseline/Current dates entered at left. Do not manually shade these cells.
GROUP 1: PROJECT DESIGN & INITIATION
| 1 | Subrecipient award and project initiation | Initiate project upon award and prepared for next steps |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 1
| 2 | Subrecipient obtains expertise for NEPA, NHPA, and Section 7 reviews | Retain a qualified environmental consultant to support NEPA, NHPA, and Section 7 reviews |  | 2026-09-02 | 2026-10-02 | 2026-09-02 | 2026-11-02 | 44
| 3 | NEPA Project Area Approval | Submit project description and maps to KOBD | KOBD requested a revised project map; approval slipped into mid-March. | 2026-06-05 | 2026-07-05 | 2026-06-05 | 2026-07-05 | 21
GROUP 2: TRIBAL COORDINATION & AGENCY ENGAGEMENT
| 4 | Subrecipient provides project information to KOBD to initiate Tribal notification through the Project Description tab of the KOBD ESAPTT Screening Questionnaire | Provide required project information to KOBD early so NTIA can initiate Tribal notification upon creation of the ESAPTT project record |  | 2026-09-20 | 2026-10-20 | 2026-09-20 | 2026-10-20 | 22
| 5 | Pre-application meetings with permitting agencies | Schedule pre-application meetings with KDOT, county road departments, and other agencies/entities to confirm right-of-way permit requirements |  | 2026-07-20 | 2026-08-20 | 2026-07-20 | 2026-09-20 | 45
GROUP 3: ENVIRONMENTAL REVIEW & CONSULTATIONS
| 6 | Conduct resource screening to support completion of the Extraordinary Circumstances tab of the ESAPPT Screening Questionnaire | Use APPEIT tool and other available desktop resources to complete initial screening of extraordinary circumstances |  | 2026-09-15 | 2026-10-15 | 2026-09-15 | 2026-10-15 | 23
| 7 | Conduct ESA Section 7 obligations (NTIA “No Effect” list, IPaC, Biological Assessment, USFWS-Kansas / KDWP consultation) | Check NTIA's “No Effect” list; use IPaC and prepare a brief Biological Assessment, routed through KOBD for pre-screening before submission to USFWS-Kansas and KDWP |  | 2026-10-01 | 2026-11-15 | 2026-10-01 | 2026-12-15 | 54
| 8 | Conduct Section 106 process, including Kansas SHPO consultation | Complete records check of Area of Potential Effects; submit Section 106 package to Kansas SHPO via the Kansas Review & Compliance portal, routed through KOBD for pre-screening first |  | 2026-10-01 | 2026-11-01 | 2026-10-01 | 2026-11-22 | 37
| 9 | Screen and address water resources (wetlands, streams, floodplains); pursue USACE Section 404/408 and KDHE Section 401 authorizations as applicable | Use NWI, NHD, hydric soils, and FEMA floodplain data to identify potential impacts to wetlands, streams, floodplains; Prepare a summary waters resources report to identify project intersections and associated BMPs to avoid impacts or needed permits | Wetland delineation required to identify wetland boundaries for avoidance planning or permitting if avoidance cannot be avoided; Requires an additional one month to complete delineation | 2026-10-01 | 2026-11-01 | 2026-10-01 | 2027-02-25 | 106
| 10 | NEPA level determined | Based on the information provided, NTIA determined the project qualifies for a Categorical Exclusion |  | 2026-11-15 | 2026-12-15
| 11 | Complete and submit EHP package (ESAPTT Screening Questionnaire) to KOBD | Complete all three tabs of the ESAPTT Screening Questionnaire and submitted supporting docuentation to KOBD |  | 2026-12-15 | 2027-01-15
| 12 | Receive NEPA decision document / Notice to Proceed | Await NTIA's Final NEPA Decision Memo and KOBD's Notice to Proceed |  | 2027-04-15 | 2027-05-15
GROUP 4: PERMITS & AUTHORIZATIONS
| 13 | Identify required local, state, and federal permits | Identified needed permits from KDOT, BNSF, and local power company for pole attachments; Gathering info to begin permit applications |  | 2026-10-01 | 2026-11-01
| 14 | Begin state and local permit applications | Determined that KDOT, BSNF, and pole-attachment permits are required; start/end dates for this row are for all state/local permits; see individual permit schedules below |  | 2026-11-15 | 2027-02-25
| 15 | Finalize remaining permits and private authorizations | USACE Section 408 Permit for bridge attachment |  | 2027-01-15 | 2027-03-25
Once specific permits or other activities have been identified, populate one row below for each individual permit or activity (e.g., a KDOT permit, a local utility permit). Do not insert or remove rows.
|  | Permit 1: [specify — e.g., KDOT Utility Accommodation Permit] | KDOT utility accommodation permit for 25 miles of fiber along I-70 |  | 2026-11-15 | 2027-01-15
|  | Permit 2: [specify — e.g., local/county right-of-way permit] | BSNF Utility permit for 3 railroad crossings |  | 2026-11-15 | 2027-01-15
Permit 3: [specify — e.g., utility pole attachment permit]
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Activity name
Legend
Subrecipient input cell
Activity group / phase header
Activity active in both the Baseline and Current schedule
Activity active in the Current schedule only (added since Baseline — e.g., due to a delay)
Activity was active in the Baseline schedule only (no longer part of the Current schedule)
Example placeholder row — copy, rename, and fill in for each specific permit
Do not insert or delete rows — this may cause formatting and formula errors.
Baseline Start/End: enter once, when the schedule is first set, and do not change. Current Start/End: update whenever the schedule changes. Comparing the two is what drives the automatic shading above.
Formulas:
Duration (business days) = IF([Current End]="","",NETWORKDAYS([Current Start],[Current End]))

## Subrecipient Milestone Schedule
Kansas BEAD Milestone Schedule
In addition to identifying specific deadlines and durations, the Subrecipient must also provide a narrative (as relevant) describing the completion of consultations, NEPA and Section 106 reviews, and submission of EHP documentation. This schedule reflects NTIA's preferred milestone schedule format: timeframes are tracked in months relative to project award, rather than calendar dates. A Milestone Schedule for a BEAD program project may include additional activities not represented on this sample schedule; populate applicable information in empty, pre-formatted rows below as needed. Finally, a Milestone Schedule must be updated as needed.
Project Start Date:
Project Name:
BEAD Project ID:
NEPA Project ID #:
[10 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
[10 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[10 empty] | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
| # | Activity | Narrative | Remarks | Baseline Start | Baseline End | Current Start | Current End | Duration (business days) | 2026-01-01: Activity Timeline — shading is automatic based on the Baseline/Current dates entered at left. Do not manually shade these cells.
GROUP 1: PROJECT DESIGN & INITIATION
| 1 | Subrecipient award and project initiation
| 2 | Subrecipient obtains expertise for NEPA, NHPA, and Section 7 reviews
| 3 | NEPA Project Area Approval
GROUP 2: TRIBAL COORDINATION & AGENCY ENGAGEMENT
| 4 | Subrecipient provides project information to KOBD to initiate Tribal notification through the Project Description tab of the KOBD ESAPTT Screening Questionnaire
| 5 | Pre-application meetings with permitting agencies
GROUP 3: ENVIRONMENTAL REVIEW & CONSULTATIONS
| 6 | Conduct resource screening to support completion of the Extraordinary Circumstances tab of the ESAPPT Screening Questionnaire
| 7 | Conduct ESA Section 7 obligations (NTIA “No Effect” list, IPaC, Biological Assessment, USFWS-Kansas / KDWP consultation)
| 8 | Conduct Section 106 process, including Kansas SHPO consultation
| 9 | Screen and address water resources (wetlands, streams, floodplains); pursue USACE Section 404/408 and KDHE Section 401 authorizations as applicable
| 10 | NEPA level determined
| 11 | Complete and submit EHP package (ESAPTT Screening Questionnaire) to KOBD
| 12 | Receive NEPA decision document / Notice to Proceed
GROUP 4: PERMITS & AUTHORIZATIONS
| 13 | Identify required local, state, and federal permits
| 14 | Begin state and local permit applications
| 15 | Finalize remaining permits and private authorizations
Once specific permits or other activities have been identified, populate one row below for each individual permit or activity (e.g., a KDOT permit, a local utility permit). Do not insert or remove rows.
Permit 1: [specify — e.g., KDOT Utility Accommodation Permit]
Permit 2: [specify — e.g., local/county right-of-way permit]
Permit 3: [specify — e.g., utility pole attachment permit]
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Activity Name
Legend
Subrecipient input cell
Activity group / phase header
Activity active in both the Baseline and Current schedule
Activity active in the Current schedule only (added since Baseline — e.g., due to a delay)
Activity was active in the Baseline schedule only (no longer part of the Current schedule)
Example placeholder row — copy, rename, and fill in for each specific permit
Do not insert or delete rows — this may cause formatting and formula errors.
Baseline Start/End: enter once, when the schedule is first set, and do not change. Current Start/End: update whenever the schedule changes. Comparing the two is what drives the automatic shading above.
Formulas:
Duration (business days) = IF([Current End]="","",NETWORKDAYS([Current Start],[Current End]))